HOW TO USE THIS TEMPLATE:

Once your plan is completed, check the document against the following Quality Criteria:

- Does the document correctly represent the project?

- Does it show a viable, achievable project that is in line with corporate strategy or overall programme needs?

- Is the project organisation structure complete, with names and titles?

- Have all the roles been considered?

- Does it clearly show a control, reporting and direction regime that is implementable and appropriate to the scale, business risk and business importance of the project?

- Is the project organisation structure backed up by agreed and signed job descriptions?

- Are the relationships and lines of authority clear?

- Do the controls satisfy any delegated assurance requirements?

- Is it clear who will administer each control?

PROJECT DOCUMENTATION

PROJECT PLAN

| Project: | Smart School Management System |
| --- | --- |
| Release: | Phase 1: Pilot |
| Date: | 17 June 2026 |
| PM Approach: |  |
| Author: | G.G.M.P. Kusumsiri |
| Owner: | G.G.M.P. Kusumsiri (Start-Up Manager) |
| Client: | G.G. Kusumsiri, Principal (SLPS-1), CP/KOT/Delta Gemunupura College, Pussellawa |
| Document Ref: |  |
| Version No: |  |

# 1	Plan Document History

## 1.1	Document Location

This document is only valid on the day it was printed.

The source of the document will be found on the project's PC in location C:\Users\User\Documents\GitHub\delta-gemunupura-dbms-2026\agile project

## 1.2	Revision History

Date of this revision: 17 June 2026

Date of Next revision: 17 July 2026

| Revision date | Previous revision date | Summary of Changes | Changes marked |
| --- | --- | --- | --- |
|  |  | First issue |  |

## 1.3	Approvals

This document requires the following approvals.

Signed approval forms are filed in the Management section of the project files.

| Name | Signature | Title | Date of Issue | Version |
| --- | --- | --- | --- | --- |
| G.G. Kusumsiri |  | Principal / Client | 17 June 2026 | 1.0 |
| U.G.C. Nayanathara |  | Project Manager | 17 June 2026 | 1.0 |
| T.H. Samaranayake |  | Quality Manager | 17 June 2026 | 1.0 |

## 1.4	Distribution

This document has been distributed to:

| Name | Title | Date of Issue | Version |
| --- | --- | --- | --- |
| G.G. Kusumsiri | Principal / Client | 17 June 2026 | 1.0 |
| G.G.M.P. Kusumsiri | Start-Up Manager (also Developer Team Leader) | 17 June 2026 | 1.0 |
| U.G.C. Nayanathara | Project Manager (also Developer) | 17 June 2026 | 1.0 |
| T.H. Samaranayake | Quality Manager (also Developer) | 17 June 2026 | 1.0 |
| G.M.D. Fernando | Risk Manager (also Developer) | 17 June 2026 | 1.0 |
| N.D. Ranasinghagei | Scheduling Manager (also Developer) | 17 June 2026 | 1.0 |

# 2	Table of Contents

Page

### 1	Project Initiation Document History						1

1.1	Document Location								1

1.2	Revision History

1.3	Approvals

1.4	Distribution

### 2	Table of Contents

### 3	Purpose of Document

### 4	Background

### 5	Project Definition

5.1	Project Objectives

5.2	Defined Method Approach

5.3	Project Scope

5.4	Project Deliverables and/or Desired Outcomes

5.5	Exclusions

5.6	Constraints

5.7	Assumptions

5.8	Legal and ethical

### 6	Project Organisation Structure

6.1	Project Management Team Structure

6.2	Job Descriptions

### 7	Communication Plan

### 8	Project Quality Plan

### 9	Project Controls

### 10	Initial Risk Log

# Project Plan

## 3	Purpose of Document

The purpose of this document is to define the project, to form the basis for its management and the assessment of overall success.

## 4	Background

CP/KOT/Delta Gemunupura College (Pussellawa) currently manages student, staff, examination, and inventory records through manual processes and disconnected spreadsheets. On 12 June 2026, Principal G.G. Kusumsiri issued a formal mandate requesting a comprehensive cloud-based School Management System as a pilot at the school.

The mandate requires web, Android, and iOS access; core modules for students, staff, inventory, examinations, and timetables; real-time performance analytics when term test marks are entered; parental engagement through a dedicated parent portal; and strict role-based access control for principal, technical officer, vice principal, teachers, students, and parents.

A Project Brief (CS11) was prepared Starting Up a Project. This Project Plan defines how the student development team will design, build, test, and hand over the Smart School Management System. The proposed solution will use Next.js, Firebase (Authentication and Firestore), and cloud-hosted hosting. Timetable management and a native iOS application are planned for a later phase.

Business case: once delivered, the system will reduce administrative burden, improve accuracy of academic records, enable faster parent communication, and provide leadership with school-wide visibility addressing a missing component of the school's digital strategy.

## 5	Project Definition

### 5.1	Project Objectives

Project delivery objectives

- Complete Phase 1 pilot go-live at Delta Gemunupura College by August 2026.

- Deliver a production-ready web PWA and official Android APK without Play Protect warnings.

- Provision admin accounts and onboard at least 10 staff and 50 student/parent logins.

- Establish a CI pipeline (lint, unit tests, production build) that passes on every release.

- Design and publish Firestore security rules aligned with the planned role-based access model.

Project outcome objectives

- Reduce time to enter and retrieve term test results by at least 50% vs manual methods.

- Teachers retrieve student contact details and results within 30 seconds of login.

- Parents gain same-day visibility of published exam results after marks are entered.

- System auto-calculates grades, pass/fail status, and class ranks when results are saved.

- Teachers restricted to assigned grades; Vice Principal will have view-only access to all modules.

- Maintain reliable uptime for the hosted web application.

### 5.2	Defined Method of Approach

The project will be governed for documentation, roles, controls, and risk management. Delivery will follow an Agile iterative approach: two-week sprints, demonstrable software at the end of each sprint, sprint reviews with the Project Manager and Quality Manager, and backlog prioritisation aligned to the principal's mandate.

Proposed technical approach: Next.js App Router, Firebase Authentication and Firestore, Tailwind CSS, role-based access controls mirrored in Firestore security rules, GitHub Actions CI/CD, and a Bubblewrap Trusted Web Activity for Android distribution. Application development will be carried out by the developer team, led by G.G.M.P. Kusumsiri (Developer Team Leader), with U.G.C. Nayanathara, T.H. Samaranayake, G.M.D. Fernando, and N.D. Ranasinghagei as developers.

### 5.3	Project Scope

MoSCoW prioritisation:

| Priority | Scope items |
| --- | --- |
| Must have | - Student Management (CRUD, search, CSV import, PDF export) - Staff Management (CRUD, Google Form CSV/XLSX import) - Examination Management (create exams, enter results, auto-grading, ranks, report export) - Inventory Management (asset register CRUD) - User Management (principal, technical officer, VP, teacher, student, parent logins) - Web PWA with install support - Android official APK (Trusted Web Activity) - Real-time performance analytics on data entry - Parent portal (view child's progress and exam results) |
| Should have | - Quick PIN login for mobile users - Biometric unlock on installed PWA - WhatsApp integration for sharing student credentials - Examination information reports for leadership |
| Could have | - Timetable Management module - Teacher performance percentage dashboards - Bulk SMS notifications to parents |
| Won't have (Phase 1) | - Native iOS App Store application (Safari PWA install only) - Full offline database synchronisation - Integration with government EMIS or national exam systems - Fee/billing or payroll modules |

### 5.4	Project Deliverables and/or Desired Outcomes

- Production web application (PWA) for school use

- Android APK (Trusted Web Activity) with install guide

- Firebase project with Authentication, Firestore, security rules, and composite indexes

- Source code repository with CI workflow

- User documentation: system guide, Android install guide, and iOS install instructions

- Sample CSV templates for student, staff, exam results, and inventory import

- Admin setup utilities for creating the first principal account and provisioning student logins

- Project documentation: Project Mandate, Project Brief, and this Project Plan

- Role-based dashboards and module screens for all mandated user types

- PDF export for student/staff profiles and examination reports

### 5.5	Exclusions

- Native iOS application distributed through the Apple App Store

- Timetable scheduling module (deferred to Phase 2)

- Hardware procurement (cloud hosting only)

- Ongoing Firebase and hosting subscription costs beyond pilot period

- On-site IT support contract after handover

- Data migration from legacy paper records beyond CSV import tooling

- Sinhala/Tamil full UI localisation (English UI with Sri Lankan data formats)

### 5.6	Constraints

- Pilot must be usable before Term 3 2026 examinations where possible

- Team size: 5 student project roles; G.G.M.P. Kusumsiri is Start-Up Manager and Developer Team Leader; all other team members are developers

- Budget: free tier / low-cost cloud (Firebase, affordable hosting)

- No dedicated full-time developer staff at school post-handover

- Must comply with data protection expectations for student PII

- Must not store passwords or PIN hashes in client-accessible Firestore documents

- Android distribution must use signed official APK, not Chrome WebAPK

### 5.7	Assumptions

- School has reliable internet connectivity for daily use

- Principal and technical officer assign time for UAT and acceptance sign-off

- Teachers receive short orientation on login and result entry

- Firebase service account and QUICK_PIN_PEPPER will be configured for production hosting

- GitHub Actions secrets will be available for Android APK builds

- Student admission numbers and staff IDs are accurate for linking logins

- Parents have smartphones capable of installing PWA or Android APK

5.8	Legal and ethical

Legal

- Personal data (student NIC, parent contact, exam results) must be processed lawfully; access limited by role.

- Firebase and cloud hosting data processing terms apply; school remains data controller for student records.

- APK signing and Digital Asset Links must associate the Android app with the school domain.

Ethical

- Equitable access: parents without smartphones are not excluded (paper reports remain available).

- Student photos and disability notes are sensitive visible only to authorised staff.

- Inactive accounts must be disabled promptly when staff leave or students transfer.

- Examination data must not be altered without an audit trail in Firestore records.

## 6	Project Organisation Structure

### 6.1	Project Management Team Structure

| Role | Name | Responsibility |
| --- | --- | --- |
| Executive / Client | G.G. Kusumsiri | Principal: project mandate, scope approval, and final acceptance |
| Project Manager | U.G.C. Nayanathara (also Developer) | Day-to-day control, sprints, reporting, stakeholder liaison, application development |
| Start-Up Manager | G.G.M.P. Kusumsiri (also Developer Team Leader) | Client liaison, mandate documentation; will lead developer team and code integration |
| Quality Manager | T.H. Samaranayake (also Developer) | Will own CI checklist, UAT, acceptance sign-off support, and application development |
| Risk Manager | G.M.D. Fernando (also Developer) | Will maintain risk log, monthly reviews, and application development |
| Scheduling Manager | N.D. Ranasinghagei (also Developer) | Will maintain milestone plan, sprint calendar, and application development |

### 6.2	Individual Role Descriptions

| Role | Assigned to | Job description |
| --- | --- | --- |
| Project Manager | U.G.C. Nayanathara (also Developer) | Will plan sprints, run stand-ups, deliver demos, maintain documentation, manage releases, liaise with the principal, and implement assigned application features. |
| Start-Up Manager | G.G.M.P. Kusumsiri (also Developer Team Leader) | Will maintain mandate documentation; liaise with the principal: facilitate demos and feedback; lead the developer team; assign development tasks; review and integrate code; define application architecture; support CI builds. |
| Quality Manager | T.H. Samaranayake (also Developer) | Will own test strategy, CI checklist, UAT scripts, and acceptance sign-off records; implement assigned features and support testing. |
| Risk Manager | G.M.D. Fernando (also Developer) | Will maintain risk log, facilitate monthly risk reviews, track mitigations; implement assigned features and support testing. |
| Scheduling Manager | N.D. Ranasinghagei (also Developer) | Will maintain milestone plan, sprint calendar, and track slippage; implement assigned features and support testing. |

## 7	Communication Plan

| Activity | Audience | Frequency | Owner |
| --- | --- | --- | --- |
| Weekly sprint stand-up | Development team | 30 minutes | Scheduling Manager (minutes) |
| Fortnightly demo | Principal (G.G. Kusumsiri) and Start-Up Manager | 45 minutes | U.G.C. Nayanathara (sprint increments) |
| Sprint status report | Project Manager | Sprint report - at the end of each sprint | U.G.C. Nayanathara |
| Risk register review | Risk Manager + team | Monthly | G.M.D. Fernando |
| Quality release checklist | Quality Manager | Before each release | T.H. Samaranayake |
| Escalation (>48h blocker) | Principal (G.G. Kusumsiri) via Start-Up Manager | As needed | G.G.M.P. Kusumsiri |

## 8	Project Quality Plan

| Area | Standard / activity | When | Owner |
| --- | --- | --- | --- |
| Code quality | TypeScript + ESLint clean on CI | Every PR | T.H. Samaranayake, G.G.M.P. Kusumsiri |
| Unit tests | Unit tests for role-based access, grading, and PIN validation | Every PR | T.H. Samaranayake |
| Security | Firestore rules aligned with planned role matrix | Each release | T.H. Samaranayake |
| CI build | Automated lint, test, and build in GitHub Actions | Every PR | T.H. Samaranayake, G.G.M.P. Kusumsiri |
| Code review | Review pull requests before merge to main | Every PR | T.H. Samaranayake |
| UAT | Manual checklist per module before pilot | Pre-go-live | T.H. Samaranayake |
| Acceptance | Acceptance criteria checklist and sign-off coordination | Phase 1 end | T.H. Samaranayake |

## 9	Project Controls

Controls

- Time:N.D. Ranasinghagei (Scheduling Manager) maintains sprint plan and milestone tracker.

- Quality: CI pipeline and Quality Manager checklist run before each release.

- Risk: Monthly risk log review; new risks logged within 24 hours of identification.

- Scope: Change requests will require approval from the principal (G.G. Kusumsiri), coordinated by the Start-Up Manager (G.G.M.P. Kusumsiri), when MoSCoW 'Must' items are affected.

- Configuration: Git tags for releases; production releases from main branch only.

- Security: Firestore rules publish checklist; no secrets committed to repository.

Monitoring

- GitHub Actions CI status on every push and pull request.

- Firebase Console usage and Authentication user counts.

- Application health checks and planned production support endpoint.

Exception process

- If sprint commitment slips more than 3 days, PM reports to Scheduling Manager with a recovery plan.

- If a critical defect is found after go-live, use a hotfix branch; Quality Manager approves emergency release.

- If the Principal changes mandate scope, update the Project Brief and re-baseline this plan.

## 10	Initial Risk Log

| ID | Risk description | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| R01 | Internet dependency: no offline database | High | Plan PWA offline page; communicate network requirement to users | G.M.D. Fernando |
| R02 | Firebase cost overrun at scale | Medium | Monitor usage; optimise queries; publish composite indexes | G.M.D. Fernando |
| R03 | Teachers resist adopting new system | Medium | Training session; Quick PIN login; parallel paper records during pilot | G.M.D. Fernando |
| R04 | Incorrect RBAC exposes student data | High | Design Firestore rules and access-control tests; verify VP view-only | G.M.D. Fernando |
| R05 | iOS users expect native App Store app | Low | Provide iOS install guide; document exclusion in Project Brief | G.M.D. Fernando |
| R06 | Android Play Protect warnings (WebAPK) | Medium | Plan official signed Android APK; document install steps for IT | G.M.D. Fernando |
| R07 | Service account / PIN pepper misconfigured for production | High | Use production environment setup checklist; planned health-check endpoint | G.M.D. Fernando |
| R08 | Timetable module not ready for pilot | Medium | Defer to Phase 2; agree scope with Principal | G.M.D. Fernando |
| R09 | Student login linking errors (wrong admission number) | Medium | Plan bulk provision process; admin verification before go-live | G.M.D. Fernando |
| R10 | Academic calendar pressure | Medium | Prioritise exam module in sprint plan; agile reprioritisation each sprint | G.M.D. Fernando |